3 Year Pupil Premium strategy plan 2019-2022 (yearly review 2020/2021)

| Summary information |  |  |  |
| --- | --- | --- | --- |
| Pupil Premium Strategy Plan | - Guildford Grove Primary School |  |  |
| - CURRENT PUPIL INFORMATION [2019 – 2020] |  |  |  |
|  |  | Total pupil premium budget: | - £180,500 |
| Number of pupils eligible for pupil premium: | 136 | Amount of pupil premium received per child: | £1,320 |
| Current pupil information [2020 – 2021] |  |  |  |
| Total number of pupils: | 360 | Total pupil premium budget: | £189,645 |
| Number of pupils eligible for pupil premium: | 141 | Amount of pupil premium received per child: | £1,345 |

| Cohort information |  |  |
| --- | --- | --- |
| CHARACTERISTIC | Number of group 2020- 2021 | Percentage of group 2020- 2021 |
| Boys | 168 | 47% |
| Girls | 192 | 53% |
| SEN support | 106 (22 EHCP + 84 SEND support) | 29.4% |
| EHC plan | 22 | 6% |
| EAL | 56 | 15.5% |

Assessment data

| End of KS1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2016 – 2017 |  |  |  |  |  |  |  | 2017 – 2018 |  |  |  |  |  |  |  | 2018 – 2019 |  |  |  |  |  |  |  |  |  |
|  | National Average |  | Non-Pupil Premium (33) |  | Pupil- Premium (17) |  | Pupil premium pure |  | National Average |  | Non-Pupil Premium (35) |  | Pupil- Premium (16) |  | Pupil premium pure |  | National Average |  | Non-Pupil Premium (33) |  | Pupil- Premium (19) |  | Pupil premium pure (12) |  |  |  |
| % achieving expected standard or above in reading, writing and maths | * |  | 42% |  | 35% |  | * |  | * |  | 46% |  | 44% |  | * |  | 65% |  | 55% |  | 53% |  | 83% |  |  |  |
| % achieving higher standard in reading, writing and maths | * |  | 0% |  | 0% |  | * |  | * |  | 0% |  | 6% |  | * |  | 11% |  | 9% |  | 0% |  | * |  |  |  |
| % achieving expected standard+ in reading | 75% |  | 52% |  | 41% |  | 50% |  | 75% |  | 51% |  | 56% |  | 69% |  | 75% |  | 73% |  | 63% |  | 92% |  |  |  |
| % achieving higher standard in reading | * |  | 9% |  | 6% |  | 7% |  | 26% |  | 3% |  | 13% |  | 15% |  | 25% |  | 27% |  | 16% |  | 25% |  |  |  |
| % achieving expected standard+ in writing | 68% |  | 42% |  | 35% |  | 43% |  | 70% |  | 51% |  | 44% |  | 54% |  | 69% |  | 55% |  | 58% |  | 92% |  |  |  |
| % achieving higher standard in writing | * |  | 0% |  | 6% |  | 0% |  | 16% |  | 0% |  | 6% |  | 8% |  | 15% |  | 9% |  | 0% |  | 0% |  |  |  |
| % achieving expected standard+ in maths | 75% |  | 48% |  | 59% |  | 64% |  | 76% |  | 60% |  | 56% |  | 69% |  | 76% |  | 70% |  | 53% |  | 83% |  |  |  |
| % achieving higher standard maths | * |  | 6% |  | 6% |  | 7% |  | 22% |  | 0% |  | 6% |  | 8% |  | 22% |  | 12% |  | 11% |  | 17% |  |  |  |
| % achieving expected in science | 82% |  | 52% |  | 53% |  | 64% |  | 83% |  | 57% |  | 56% |  | 69% |  | 82% |  | 70% |  | 53% |  | 83% |  |  |  |
| End of KS2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 2016 – 2017 |  |  |  |  |  |  |  | 2017 – 2018 |  |  |  |  |  |  |  | 2018 – 2019 |  |  |  |  |  |  |  |  |
|  |  | National Average |  | Non-Pupil Premium (28) |  | Pupil- Premium (31) |  | Pupil premium pure |  | National Average |  | Non-Pupil Premium (23) |  | Pupil- Premium (21) |  | Pupil premium pure |  | National Average |  | Non-Pupil Premium (34) |  | Pupil- Premium (21) |  | Pupil premium pure (13) |  |  |
| % achieving expected standard or above in reading, writing and maths |  | 62% |  | 57% |  | 32% |  | * |  | 64% |  | 65% |  | 48% |  | * |  | 65% |  | 65% |  | 43% |  | 62% |  |  |
| % Higher standard in reading, writing and maths |  | * |  | 11% |  | 3% |  | * |  | 10% |  | 9% |  | 10% |  | * |  | 11% |  | 12% |  | 0% |  | * |  |  |
| % achieving expected standard+ in reading |  | 72% |  | 75% |  | 45% |  | 65% |  | 75% |  | 70% |  | 62% |  | 91% |  | 73% |  | 68% |  | 52% |  | 70% |  |  |
| % achieving higher standard in reading |  | * |  | 21% |  | 6% |  | 6% |  | 28% |  | 39% |  | 19% |  | 36% |  | 27% |  | 24% |  | 10% |  | 20% |  |  |
| % achieving expected standard+ in in writing |  | 76% |  | 68% |  | 55% |  | 71% |  | 78% |  | 76% |  | 52% |  | 91% |  | 78% |  | 76% |  | 62% |  | 80% |  |  |
| % achieving higher standard in writing |  | 18% |  | 14% |  | 3% |  | 0% |  | 20% |  | 26% |  | 10% |  | 18% |  | 20% |  | 18% |  | 10% |  | 10% |  |  |
| % achieving expected standard+ in GPS |  | 77% |  | 82% |  | 68% |  | 94% |  | 78% |  | 83% |  | 62% |  | 91% |  | 78% |  | 76% |  | 57% |  | 70% |  |  |
| % achieving higher standard in GPS |  | * |  | 29% |  | 10% |  | 12% |  | 35% |  | 30% |  | 19% |  | 27% |  | 36% |  | 44% |  | 29% |  | 30% |  |  |
| % achieving expected standard+ in maths |  | 75% |  | 82% |  | 65% |  | 100% |  | 76% |  | 87% |  | 67% |  | 100% |  | 79% |  | 76% |  | 57% |  | 70% |  |  |
| % achieving higher standard in maths |  | * |  | 36% |  | 13% |  | 18% |  | 24% |  | 35% |  | 10% |  | 18% |  | 27% |  | 21% |  | 14% |  | 20% |  |  |
| % achieving expected in science |  | 82% |  | 79% |  | 65% |  | 88% |  | 83% |  | 87% |  | 57% |  | 91% |  | 83% |  | 79% |  | 52% |  | 80% |  |  |

| OTHER DATA |  |  |
| --- | --- | --- |
|  | - Strengths | - Weaknesses |
| - Attendance data | - Using Study bugs app to monitor attendance. This feeds into Sims and allows all staff to monitor reasons for absences. 83% of parents are on Studybugs - SLT team monitoring attendance regularly. - IWO (Inclusion Welfare Officer) works with attendance lead to monitor children with poor attendance. - Attendance celebrated and encouraged across the school (as a whole school weekly in assembly). - Truancy alerts sent to parents to highlight when children have not been brought into school and to check reasons. | - Attendance: |
| - Behaviour | - Children know the main rule at Guildford Grove. - Staff receive training on behaviour and the importance of our behaviour system. - Research suggests that intrinsic motivation and self-determination is a key factor in success and academic achievement. - Behaviours for learning and the code of conduct are covered in assemblies. | - Number of exclusions: - Pupil premium; - Non- pupil premium. - Autumn 2020; - 0; - 3. - Spring 2021; - 0; - 0. - Summer 2021; - 0; - 0. |
| - Safeguarding | - Regular safeguarding training for all staff. - All staff actively use CPOMS to log safeguarding concerns. - An experienced safeguarding team. | - Some staff absences due to Covid. Ensure that all procedures secure when staff are off. |

|  | - Pupil premium | - Non- pupil premium |
| --- | --- | --- |
| - Autumn 2020 | - 93.1% | - 94.7% |
| - Spring 2021 | - Covid lockdown | - Covid lockdown |
| - Summer 2021 | - 93% | - 95% |

LONG-TERM PLAN (3 YEAR TIMESCALE):

At Guildford Grove, we recognise that disadvantaged can go beyond social and economic factors and that some children will face multiple disadvantages to their education. As a school, we strive to provide a culture where all children can achieve. We have the greatest ambitions of each and every child in our care so that they have the highest aspirations for their future and their life chances are enhanced. Our ambition is to improve the attainment and well-being outcomes for each disadvantaged child and for each disadvantaged child to make increased progress in their learning. Our priorities to ensure that we do this include: - To ensure high quality teaching for all pupils. At Guildford Grove, we know it is essential for all pupils to have access to high quality teaching throughout their education. We will provide quality first teaching (in line with the guidance on our School Development Plan - SDP). Teachers will receive CPD training in identified areas of need to ensure that they are able to design and deliver an engaging and enriching curriculum for all children to access. Research from Education Endowment Fund (EEF) states that, “What happens in the classroom makes the biggest difference.” They also state that, “Good teaching for all pupils has a particular benefit for disadvantaged children.” Further to this, close monitoring of each child will ensure that should they not be making at least the expected progress, that they will be supported through targeted teaching and interventions. - To ensure the mental health and well-being of our families and ensure children are ready and prepared to learn. From research, we understand the link between improved mental health and well-being and increased levels of academic achievement. Furthermore, research states that better emotional well-being is linked to better engagement in school. Therefore, we aim for our children and their families to have increased mental-health and to support their well-being in order for them to come to school and succeed in their learning and through social experiences (this follows through as one of our SDP aims). - For disadvantaged children with SEND to make good or better progress from their starting points. At Guildford Grove, a high percentage of disadvantaged children are also children with Special educational needs (SEND). All staff understand the importance of supporting the needs of each child. All staff are teachers of children with SEND and will differentiate learning to suit the capabilities and needs of each child. As a school, we will use the ‘Profile of Need’ to ensure that every child’s needs are met appropriately. Where there are gaps in progress and specific needs identified, targeted and reliable interventions will be implemented, monitored and tracked over a set period to ensure that children begin to close the gap and make at least good progress from their starting point. - To increase the engagement of all parents in school life at Guildford Grove. Research suggests that parental engagement is key in the success of children’s learning and their learning outcomes. This will support families in understanding the importance of attending consistently and arriving to school on time. Parental engagement will ensure that the school are aware of any barriers to the family so that they can be fully supported in an appropriate manner. Parents will have an increased understanding of what their child is learning at school and how to support them at home. - Improving the possibilities and life chances of all children. Research suggests that increased cultural capital supports children to succeed in life (e.g. job interviews, networking with colleagues or discussions). At Guildford Grove, we aim to increase the life chances of our disadvantaged children so that they can succeed in the future alongside their non-disadvantaged peers. We will provide children with increased opportunities to participate and engage in a wider range of enrichment activities both within curriculum time and before and after school. This will expose them to a range of unfamiliar experiences as well as providing them with the opportunity to build on their vocabulary through discussions.

| priority 1 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| - To ensure high quality teaching for all. |  |  |  |  |  |  |
| Objectives/ intended outcome | Actions to be taken and rationale for actions. | By whom | Review dates | Resources needed | Progress indicators | Outcome |
| To increase the percentage of Pupil Premium children achieving EXS in reading, writing, maths and combined at the end of KS2. | Implement new broad, fluid, and progressive curriculum (across two years). | Curriculum lead Supported by subject leads Implemented by all staff | Short review: Half-termly Full review: Summer 2021 | Staff meetings completing curriculum design. Subject leads to support planning of curriculum. | INTENT: Curriculum is well-sequenced and clearly builds on children’s previously taught skills. IMPACT: Progressions of skills across the school is clear. | Summer 2021 Some parts of the curriculum have been effectively implemented but others have been impacted by COVID. Parts of the curriculum have had to be revisited due to gaps identified in many of the children’s learning. Staff meetings to plan and design curriculum have been taking place. A particular focus on Literacy in the Autumn Term 2021. |
|  | Reading CPD training for all staff using research from the Literacy Shed and the VIPERS model Monitoring of the teaching of reading (linked to SDP). | Literacy leads | Review: Summer 2021 | Training sessions Training resources Pie Corbett reading spine | INTENT: reading is taught across the school with a consistent approach using a structured strategy. (EEF state that reading comprehension strategies can support progress by +5) IMPACT: children have an improved understanding of reading VIPERS and key reading skills. Children are able to identify skills and use them more independently. | Summer 2021 VIPERS are being used across the school to support the teaching of reading. Pie Corbett reading spine has been purchased. Monitoring needs to continue in the Autumn Term 2021 as COVID limited lesson observation and opportunities to observe. Most children have an increased understanding of the VIPERS. Evidence of the VIPERS being used across the school in planning. |
|  | To raise the profile of reading across the school by identifying and implementing key texts across the curriculum. | Literacy leads Curriculum lead | Implement: Autumn 2020 Review Summer 2021 | Key texts to be purchased across the school to enrich learning and a broad range of curriculum areas. Delight reading book fayre. | INTENT: Children are more engaged in reading and have more opportunities to read for a range of purposes. IMPACT: children are more engaged in reading and read with greater fluency and understanding. Children’s vocabulary increases across a range of subject areas. Children are able to apply their new vocabulary in their learning and when speaking. | Summer 2021 A range of key texts have been purchased and placed in class reading corners to expose children to a wider range of texts. Some topics have been planned for with a focus on key texts. Key text section implemented on newly implemented planning format. Next steps: Check for effectiveness and consistency of use across the school. |
|  | Train staff and use SIMs tracking system to log and monitor PP children’s attainment and progress and identify children who are not making expected progress. | Assessment leads | First Review: Summer 2021 | SIMS login and data SIMS support booklet Staff training | INTENT: Staff have a better understanding of how to use SIMS and can use this to support data analysis. IMPACT: Staff are able to use data more easily to access information about their children and track their progress in learning. SIMs data information to be used at pupil progress meetings to ensure and track progress across the Key Stages. | Summer 2021 Staff training took place to implement the use of SIMS as a monitoring system. All teaching staff were able to use SIMS to input data including both teacher assessed data and Rising Stars data. Teaching staff were able to use data to discuss children at end of term pupil progress meetings. |
|  | For year 6 children to spend more time directly working with an adult to provide children with more regular teacher time and personalised feedback to support progress. | Year 6 team | Review: Summer 2021 | 3rd Teacher intervention in year 6. Maths teacher to lead a flexible group 2 days per week. Literacy lead to lead flexible a group 2 days per week. | INTENT: for adults to target flexible groupings of children across the year to close the gap in maths and literacy. (EEF – targeted feedback can improve performance by +8. Also, EEF – Targeted small group interventions have the potential for the largest immediate impact on attainment). IMPACT: Children across the year group will benefit from smaller class numbers and more opportunities to work with an adult. | Summer 2021 2020 – 2021: Third teacher math group supported 8 children per class from September 2020- December 2021. Supported targeted children with closing the gap. March - July 2021: Support then moved to year 5 literacy lessons as a high proportion of Year 5 children did not access literacy learning online during lockdown. Targeting children in a small group meant that children were able to receive more direct and targeted feedback at the point of learning. 2020 – 2021: Year 6 literacy third teacher supported teaching in school across the year. Less children engaged in the literacy learning whilst at home. When children returned following the Spring Term 2021 lockdown, children benefited from additional adult support to close gaps. |
|  | Restructuring of the EYFS classes to run as a separate nursery and reception group. To embed a smooth transition for disadvantaged children from EYFS to KS1. Started in 2019. | EYFS lead EYFS team | First Review: Summer 2021 Second review: Summer 2022 | Physical changing of rooms and reorganising resources and curriculum. | INTENT: EYFS children are more prepared for KS1. Children make a smooth transition from EYFS into KS1. IMPACT: 2021/2022: KS1 (who attended GG during EYFS) have a higher percentage of children working at EXS standard. | Summer 2021: EYFS children had a very disruptive year. Due to long periods of not attending during their Reception year, year 1 supported children by providing them with a continuous provision to ensure that their Early Years targets were secure. This is being repeated this year due to the large periods of time which many children were not at school. Next step: Review this year following a full year of children in provision. |

| PRIORITY 2 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| - To ensure the well-being of all our families and ensure children are ready and prepared to learn. |  |  |  |  |  |  |
| Objectives | Actions to be taken and rationale for actions. | By whom | By when | Resources needed | Progress indicators | Outcome |
| To improve the emotional, mental and physical well-being of all Pupil-Premium pupils and their families to ensure that they are ready to learn. | Home School Link Worker (HSLW) to support children and families who have a barrier to succeeding or a barrier to being in school. HSLW to work with children and families who need emotional support or who are near crisis point. | HSLW (monitored by QB) | Review: Summer 2021 | Full-time HSLW HSLW resources to carry-out successful practice. | INTENT: HSLW will support children and families who are facing crisis point or close to crisis point. To reduce barriers which may be preventing children from coming to school or succeeding at school. IMPACT: HSLW worker will support and implement prevention strategies for children and their families with the aim of children and families not going into crisis point. Families to be supported so that a fewer number of families go into crisis. | Summer 2021: HSLW along with support from the wider school team was able to provide support for many pupils and families. Continuing to work with the local social care team to support high profile children. Providing financial support advice to families in need. Working with families who have mental health needs to provide parenting advice, mental health advice and signposting for additional support. Next steps: Deputy HSLW employed. HSLW to disseminate and teach Deputy HSLW. Deputy HSLW to shadow. |
|  | To implement an updated, current and enriched PSHE curriculum which meets the needs of our cohort of children. To teach children about changes in society and to increase children’s understanding of mental health. | PSHE lead | Review: Summer 2021 | PSHE association access for all teachers. PSHE curriculum updated training for all teachers. | INTENT: For teachers to design, plan and implement a new PSHE curriculum in line with the PSHE association guidance. IMPACT: children to report an increased understanding in their knowledge of PSHE concepts. For children to report an increased understanding of Mental Health and well-being and what this is through pupil questionnaires. | Summer 2021 Training provided for all staff. 90% of staff with access to PSHE association. Next Steps: Further training, update and reminder of delivery September 2021. Focus on the links of mental health. Mental health on the SDP. Reminders about advice to adapt to our cohorts. |
|  | To train and implement the ELSA programme across KS1 and KS2. The ELSA programme will ensure that all children are provided with an outlet to overcome barriers to learning through promoting emotional stability. | HSLW to monitor | First review: End of spring term 2021 | ELSA training ELSA trained TA time | INTENT: Children have improved emotional awareness and develop strategies to cope in challenging and identified situations. IMPACT: teaching staff to complete a pre and post intervention questionnaire. Adults to report improvements in child’s behaviours on CPOMs. Children to develop strategies to succeed without intervention support. | Autumn 2020: Updated list for ELSA provision. Two new ELSA Tas trained. Spring 2021: Some additional ELSA support and provision provided on Seesaw to children who were at home. Summer 2021: Four qualified ELSA who implement support and provision across EYFS, KS1 and KS2. Next Steps: Continued training. Consider how/ if approaches need to be updated following covid. EYFS ELSA due to leave in September. Consideration of further training. |
|  | Therapeutic Story writing: Targeted children work with a trained teaching assistant for 45minutes – 1 hour per week. | HSLW to monitor. ELSA to administer | Review: Summer 2021 | TA to administer Therapeutic story writing training for TA. | INTENT: The children develop a conversation about their feelings and emotions through writing and sharing stories. IMPACT: Children to have increased scores on post intervention questionnaire. | ELSA worked with two groups for one hour per week during the Summer term. 4 pupils from year 5. 4 pupils from year 6. |
|  | Children to be invited to lunchtime club as a calm place for them to play and have a supported and successful lunchtime. Children to attend lunchtime club if they are finding outside play challenging. | SLT to monitor | Review: Summer 2021 | Lunchtime club games and activities. Space to run lunchtime club. Lunchtime club KS1 monitor Lunchtime club KS2 monitor. | INTENT: Children are able to make good choices in a controlled and supported environment. Children’s social skills improve. Children are able to have a successful lunchtime where they engage in an activity. Children will have a more successful afternoon of learning. IMPACT: Fewer lunchtime incidents to be reported on CPOMS. | Summer 2021: Through lockdown procedures, lunchtime club was able to continue and targeted children were still able to attend. Some children with SEND benefited from spending time with a trusted adult and consistency. Other children benefited from a quiet, calm space. |
|  | Breakfast Club: Children with poor punctuality will be invited to attend breakfast club in order to get children into school on time. Disengaged families and children to be invited to attend breakfast club. Children will be invited to breakfast club to encourage children to have a positive start to their morning and fuel the children ready for a day of learning. | DH | Review: End of Spring term 2021 | Breakfast club resources (food etc). | INTENT: Children will be ready to learn as they have had a positive start to the morning. Children view school in a positive light. Children increase their physical and mental wellbeing. IMPACT: The punctuality of PP children will improve. Children speak about their positive experience at breakfast club during pupil interviews. | Summer 2021: Breakfast club provision continued following the full reopening of the school. This meant that a higher proportion of families were able to receive breakfast. Children were provided with a positive morning experience by attending breakfast club. |
|  | To raise the understanding and profile of mental health for children and families across the school. Mental Health lead and HSLW to attend training and disseminate useful strategies to whole staff. | MH lead | Review: Summer 2022 | Mental Health training (external). Mental Health training for staff. | INTENT: Staff will have a wider range of strategies to use when supporting individual children or groups of children with Mental Health concerns. IMPACT: Children will have their Mental Health concerns monitored and strategies will be put in place to remove or lower this barrier to their learning. Children with SEMH will make progress against their personalised targets set on Edukey. | Spring 2021: Additional monitoring of children and families at home delegated to teams. Summer 2021: SEND team attended Zones of Regulation training to support behaviour. Mental Health staff training postponed September 2021 ( to support new staff coming in). Next steps: Whole school training of Zones of Regulation. Staff training – Mental Health and supporting additional barriers at school. Ensure that staff are aware of any new and more prominent barriers for our families. |

| PRIORITY 3 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| - For Pupil Premium children with SEND to make good or better progress from their starting points. |  |  |  |  |  |  |
| Objectives | Actions to be taken | By whom | By when | Resources | Progress indicators | Outcomes |
| To target PP children with SEND with high quality and evidence-based interventions in order to make good or better progress from starting points. | STIPS support for behaviour and literacy. For STIPS to support teachers and Teaching Assistants to provide specific and targeted support for high need children who have specific literacy difficulties or behaviour challenges. | SENCo to co-ordinate | First Review: December 2020 Second Review: Spring 2021 | STIPS adult for Literacy. STIPS adult for behaviour. | INTENT: For teachers to effectively use and implements suggested and advised strategies to work with individual and targeted children. IMPACT: For targeted children to make progress against their specific target and be able to succeed in their mainstream classroom. | Summer 2021: STIPS support was initially undertaken online and then in class. STIPS support accessed for both literacy and behaviour for a range of SEND PP children across the school as well as providing teachers with CPD to support more familiar needs within the classroom. |
|  | To implement targeted behaviour interventions and support to ensure that children with challenging behaviour can continue to be supported and implemented in their mainstream classroom. | Lead by SLT | Review: Spring 2021 | Cover of classes | INTENT: Children who are identified with challenging behaviours to improve their behaviour. Children will be able to work successfully in class. (EEF suggests that behaviour interventions can increase learning by +3 months.) IMPACT: Children who are on SEND review meetings will successfully move through the plan and the meetings will eventually be lessened and withdrawn. | Summer 2021: Regular behaviour review meetings for targeted children allowed school teams and families to meet in order to provide small, targeted steps to be worked on both in school and at home. Regular meetings meant that children were able to meet and achieve these realistic, short-term targets in order to improve their behaviour and succeed in the classroom. |
|  | Speech and Language therapy from a qualified Speech and Language therapist. Specialist staff will work with in school staff to set personalised targets. To up-skill school staff. | Lead by the SEND team | Review: Summer 2020 | Speech and Language therapist and Speech and Language assistant (external). School TA to support. | INTENT: Children will improve their speech and language and will be more successful with their in-class learning. IMPACT: Children will make good progress in their personalised speech and language targets. | Summer 2021: Continued Speech and Language support from the SLT and the SLT TA has meant that children with specific SLT difficulties have been able to receive targeted support to make progress in their speech and language. This has also started to remove some barriers to other parts of the curriculum for some children. |
|  | Speech and language interventions/ oral language interventions: EYFS staff to be trained in NELI (The Nuffield Early Language Intervention). EYFS staff to deliver NELI intervention for targeted children. | Led by trained TA Monitored by SEND team | First review after first cycle: Summer 2021 | NELI training (alternative funding for training). PP funding used to deliver sessions in school. | INTENT: For targeted children to make good progress from their original starting point and work more in line with their non-pupil premium peers. Oral language interventions can provide +5 months progress (EEF). IMPACT: Identified children will make progress from their starting point. NELI: Improved vocabulary, listening and narrative skills in the 1st 10 weeks and improved phonological awareness and letter-sound knowledge in the second 20 weeks. | Spring 2021: Intervention was unable to take place. Summer 2021: 1 term of the intervention running. Unable to run a full cycle. Some progress made but intervention difficult to measure. |
|  | Improving Literacy interventions: Phonics and spelling interventions running across KS2 Phonics training for all staff to ensure a consistent approach. | SEND team Phonics Lead. | Review: Summer 2022 | trained TA Phonics training | INTENT: Children will begin to close gaps in their phonics and spelling knowledge. Children will begin to close gaps in their learning. IMPACT: KS1 phonics scores will increase for disadvantaged children. KS2 GAPS scores will increase. KS2 writing judgements will increase for PP children. | Autumn 2021: Phonics training for whole staff including teachers and Tas. This raised the awareness of phonics across the school and ensured that there was a focused and consistent approach. It also support teaching assistants who have led interventions. Summer 2021: Whole staff spelling training to support the implementation of a targeted approach to spelling. Additional spelling training for less confident teachers (GEP workshop led by literacy leads). |
|  | Targeted maths interventions. For teaching assistants to administer SNAP on to maths and maths intervention for targeted children. | SEND team | Review: Summer 2021 | SNAP and maths resources trained teaching assistants | INTENT: Children gain an increased understanding and knowledge in a range of core mathematical concepts. IMPACT: For targeted children to improve their scores in their age-appropriate PUMA score. | Summer 2021: Some progress made on intervention across the school. Next steps: The impact of SNAP to be reviewed. Review impact and relevance to our children. |
|  | Small group and 1:1 targeted support led by the class TA to compliment what has been taught in class (KS1 and KS2). | Class teachers Monitored by SEND team | Review: Summer 2021 | Personalised resources Trained TA | INTENT: Children to work on personalised and identified target to close the gaps in their learning. IMPACT: Children to make good progress against their personalised targets (monitored on Edukey). | Summer 2021: Small group and targeted 1:1 teaching has meant that children with increasing gaps have had time to begin to close gaps and recall previously learnt concepts. See individual provision maps of SEND children. |
|  | Small group and 1:1 targeted support led by the class teacher and TA to compliment what has been taught in class and address gaps in learning (EYFS). | Class teachers Monitored by SEND team | Review: Summer 2021 | Personalised resources for each child/ group. Trained TA | INTENT: Children to work on personalised and identified target to close the gaps in their learning. IMPACT: Children to make good progress against their personalised targets (monitored on Edukey). | Summer 2021: Small group and targeted 1:1 teaching has meant that children with increasing gaps have had time to begin to close gaps and recall previously learnt concepts. See individual provision maps of SEND children. |
|  | Implement high quality, age-appropriate reading interventions to support fluency and comprehension. Year 2 – BRP Year 3 and 4 – tailored reading intervention for fluency and comprehension Year 5 and 6 – Fresh Start | Class teachers SEND team to track progress. | Review: Summer 2021 | Reading resources Trained teaching assistants to deliver bespoke interventions. | INTENT: Targeted children from specified year groups to make at least good progress in their reading. IMPACT: Children on each intervention to make accelerated progress in their reading. Children to increase their reading age. | Spring 2021: Some targeted reading interventions continued virtually to children learning from home and in school for children who were still attending. For the children who accessed this provision at home, these children at least maintained their assessed reading level. Some children did not engage and access this provision. Summer 2021: SEND reading provisions running. Some difficulties with staffing meant that some provisions were missed. Children on different interventions reassessed to ensure closing of any new possible gaps and regression in learning. Good progress made. Small groups meant that key barriers were able to be highlighted. Next steps: Explore an alternative and more suitable reading provision for year 3 and 4. |
| To embed rigorous and robust systems that accurately identify and monitor SEND groups to ensure that they make expected or accelerated progress based on their starting points. | SEND review meetings. For SEND team to meet with class teachers to monitor the progress of SEND children. | SEND team meet with class teachers. | Review: Review termly | Class cover for review meetings | INTENT: For teachers to be provided with advice, strategies and next steps to enable children to make progress in order to close the gap. Children to increase their fluency and comprehension. IMPACT: SEND children who are not making progress are highlighted and new strategies are implemented. For PP children with SEND to make progress inline with their personalised targets. | Spring 2021: Reviewed provision and progress of children who had been accessing provision time at home. Discussed and advised on what needs to be implemented on return to school. Summer 2021: Individual discussions about children meant that teachers have time to seek additional advice and support. Next steps: Use information and trends from SEND review meetings to plan Autumn term 2021 provisions and SEND training for all staff. Link to provision maps to track targets. |
|  | Senior Leadership Team to continue to monitor and discuss PP children with multiple barriers through pupil progress meetings. | SLT to lead | Review termly | Class cover of pupil progress meetings. | INTENT: PP children to be highlighted and discussed at pupil progress meetings. IMPACT: For PP children with SEND to make progress inline with their personalised targets. | Summer 2021: Pupil premium children on pupil progress forms. Ensure that pupil premium children and included as part of target children discussion. Next steps: Pupil progress forms to be changed. Explore the use of SIMs Discover to provide up to date tracking processes. |
|  | Staff to be trained on EDUKEY to track and monitor children accessing provisions and timings of provisions. | SEND team | First review: Summer 2020 Second review: Summer 2021 | Edukey Staff training materials. | INTENT: Staff training of Edukey to understand the system and how to use it effectively. Edukey to be used as a tool to monitor school wide interventions. IMPACT: All staff to be using Edukey to monitor SEND and interventions. For SEND team to be able to use the tool to monitor interventions. | Summer 2021: Edukey has been used but some staff have found it difficult to use efficiently and regularly. Despite lots of changes with the product, printout is not friendly for parents. Next steps: School to transition away from Edukey to word template with the aim of a more user- friendly system suitable for our setting. |
|  | PP lead to meet with PP governor to discuss and highlight strengths and areas of challenge from across the school. | PP lead | Review termly | PP lead cover | INTENT: PP governor to have an increased understanding of how PP funding is used at GG. To have a good understanding and awareness of updates and changes. IMPACT: Procedures for tracking and monitoring PP children are constantly being improved. | Summer 2021: Met virtually to discuss current provision and updates. Updated PP governor with information about priorities in school and focuses for provision and curriculum planning. |
|  | PP lead and governor to stay up to date with the latest advice and recommendations. PP lead and governor to relay back useful courses and information to guide Guildford Grove PP planning. | PP lead | Review termly. | PP lead cover for meetings with governor. PP courses. | INTENT: PP governor to share updated and relevant information with the governors about PP guidance. IMPACT: All governors have an increased awareness and understanding in how PP money is spent at GG. | Summer 2021: SEND governor had been on training and was able to discuss any recent changes and updates to funding. Discussed information shared and advised and academy trust Pupil Premium meetings and the actions that Guildford Grove were planning to implement following this. |

| PRIORITY 4 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| To increase the engagement of all parents in school life at Guildford Grove |  |  |  |  |  |  |
| Objectives | Actions to be taken | By whom | By when | Resources needed | Progress indicators | Outcome |
| For families to understand the importance of being in school and attendance of all pupils to increase. | Inclusion Welfare Officer (previously EWO). The IWO to support the attendance of targeted children. The IWO will base themselves in school regularly to speak directly to parents about their attendance. IWO to make suggestions to improve attendance and monitor their progress alongside our school attendance lead and HSLW. To carry out home visits for non-attendees. | Attendance lead | Review: Spring term 2021 | IWO. Time for IWO to liaise with Attendance lead and HSLW. | INTENT: For children with poor attendance to be monitored closely and provided with strategies to improve their attendance. IMPACT: The number of children with an attendance of 95% + will increase. | Summer 2021: Less face-to-face provision during this term. Families still provided support from HSLW and Deputy-head. Meetings still held with in school to attempt to remove barriers. Some attendance links to COVID. IWO still working to support some families and school refusers. Next steps: Key focus for Autumn term 2021. IWO to be back supporting on site. |
|  | To support the tracking of attendance. Parents to logon to Studybugs and type in their child’s symptoms, Studybugs will identify whether the children should/ shouldn’t come into school. To support parents. To provide parents with a better understanding of day-to-day school life and making communication between home and school smoother. To encourage parents to sign up and engage in the app. | Attendance team | Review: July 2021 | Studybugs App CPOMS IWO | INTENT: The Studybugs app will provide parents with a better understanding of if they can/ can’t bring their children to school. To improve attendance. Teachers will be more aware of attendance trends. IMPACT: Attendance data for PP children will improve and at least be 95%. | Summer 2021: Studybugs continues to be an effective way of reporting absences of children. Helpful when higher proportion children not in school due to Covid symptoms. Used by the local secondary school so parents are not required to access more than one app. Next steps: Ensure that new intake and new joiners sign up and use appropriately. |
| To remove barriers between home and school and open lines of communication. | For HSLW to continue to work with individual children and with families. | HSLW | Review: Summer 2021 | HSLW HSLW resources and facilities. | INTENT: One of the main aims is that the work she does prevents families from getting to crisis point and thus helps remove potential barriers for learning. This includes providing families with strategies to support them with their well-being, attendance and safety. IMPACT: Families who get into crisis point will be supported. Families will be prevented from getting into crisis point. These barriers will not prevent children from coming to school and learning. | Summer 2021: Supporting a high proportion of families whose circumstances have changed during or following the lockdown. Providing parenting, mental health and financial advice and guidance. |
| To support and engage parents at the early stages of school to promote a love of learning. | To provide parental workshops for EYFS families. | EYFS team. | Review: Summer 2021 | EYFS team time out of class to deliver. | INTENT: Parent’s have a better understanding of the learning process. IMPACT: Parents will talk positively about these experiences. Parents will engage in these workshops. | Summer 2021: Online videos to support parents reading with their children. Next steps: To re-engage parents and invite them back into school when possible. |

| PRIORITY 5 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Improving the possibilities and life chances of all children. |  |  |  |  |  |  |
| Objectives | Actions to be taken | By whom | By when | Resources needed | Progress indicators | Outcome |
| To increase the cultural capital of Pupil Premium children so that they have similar experiences to their non-pupil premium peers. | Children from Year 3 and 4 work with and are visited by the Delight charity. Children have the opportunity to work with trained actresses and artists to create a performance, piece of writing or piece of artwork. | Literacy lead | Review: Summer 2021 | Delight facilitators and resources. | INTENT: Children to improve their speech and language, vocabulary and ability to interact in new and less familiar activities alongside their peers. Increased parental engagement as adults are invited to share the end product which enhances and supports pupil’s engagement in a non-threatening environment. The EEF (2020) states that Arts Participation could improve learning in maths, literacy and science. They have also reported benefits of increased well-being and more positive attitudes to learning. IMPACT: Children’s feedback to have improved following pupil tracking and questionnaires. | Summer 2021: Year 4 Delight: Delight Workshop took place remotely with children in class and children who were at home. Encouraged children to engage with home learning. Children were able to see their friends and work alongside the team from the Watts gallery via Zoom. Artwork displayed in the corridor meant that children were able to see positive impact upon return to school. |
|  | Links with University of Surrey. Children are provided with the opportunity to visit, experience and work with adults from a high-quality University. For children to work with and observe positive role models to improve their future life prospects and opportunities. For adults to share experiences about university so that the children have an increased knowledge and understanding of why university may be important to their future. | SLT to monitor. Implementation by class teachers. | Review: Summer 2021 | Subsidised by Surry University | INTENT: Children to be more familiar with higher education opportunities. Children to begin to understand some of the possibilities beyond secondary school. The EEF (2020) Children’s University project discussed promising feedback related to non-cognitive outcomes including socialising and team-work. IMPACT: Student interviews to report that children have an increased understanding of higher education. For students to have ambitious aspirations for the future. | Summer 2021: Visits throughout the year were cancelled. Staff from Surrey University were able to visit on different occasions. Summer term; year 5 reading workshop with 3 members of the University team. Children were able to work with staff to engage in reading workshops. Children positively engaged in workshops and continued to talk about the books following this. Science week workshop with the University. Meant that children were able to observe and work with real scientists to raise and develop children’s aspirations for the future. Children enjoyed seeing female and male scientists. Child quoted, “I enjoyed meeting a scientist who looked like me.” In discussions with the children, they are beginning to make links and identify what University is. |
|  | Increased links with Kings College Secondary School. Children to experience positive role models and a new setting. | Upper KS2 class teachers | Review: Summer 2022 | Links with staff at Kings College | INTENT: Children to have the ability and opportunity to use more advanced and specialist equipment (e.g. cooking facilities). To support the transition from primary to secondary school. IMPACT: Through student interviews, children to have a positive outlook on future education and feel comfortable about attending Secondary school. | Summer 2021: Restrictions have made this a challenge. Next steps: To rebuild these relationships in the academic year 2021/2022 when restrictions allow. |
|  | Funding to be provided for children in need to allow them to access a range of enrichment experiences alongside their non-pupil premium peers. For children to be able to experience rich, educational, and enhanced experiences outside and on residential trips. Funding to be provided for children in need. | HSLW to liaise and coordinate | Review: Summer 2021 | Funded externally. | INTENT: For children to have the opportunity to access rich educational experiences alongside their peers. IMPACT: Through pupil interviews, children to talk positively about trips and enrichment experiences that they have had in school. | Summer 2021: High profile families were invited to funded holiday clubs e.g. CHIPS. This allowed the children to receive a meal as well as engage in a range of structured activities throughout the day. Funding provided for trips which took place in Summer 2021. This meant that children were able to access outdoor enrichment activities which they had been deprived of particularly during lockdown. |
|  | Children to have access to free after school sports clubs to encourage social interactions, fitness, physical and mental wellbeing and the opportunity to learn new skills. For children to have the opportunity to experience elite sports events and funded trips. | P.E lead | Review: Summer 2021 | Funded by Sports Premium Partially funded through sports premium. | INTENT: Children have the opportunity to participate in a range of sports to improve their physical and mental health. Children have an increased understanding of a range of sports and are able to talk about competition. More children will be exposed to elite sport and positive role models. IMPACT: An increased number of pupil premium children will attend clubs and sports school trips. |  |
|  | For the children to be engaged in a range of shows and performances across the school. With an increased exposure to music opportunities, drama, and arts. | Foundation curriculum leads | Review: Summer 2021 | Teachers to lead. | INTENT: disadvantaged children from across the school will be exposed to a high proportion of performance opportunities. This will increase their understanding of the arts and improve their language and vocabulary skills. EEF (2020) discuss the improvements between drama and writing as well as an increase in positive attitudes to learning and increased well-being. IMPACT: Through pupil interviews, children to talk positively about these experiences and their impact on their confidence and self-esteem. | Summer 2021: GGGT meant that children were able to perform and thrive on an outdoor stage to an audience. Students in year 5/6 were able to watch a Guildford Shakespeare performance so that they could engage in being and audience and interact with live actors. This gave children a purpose. |

Estimated budget for the year 2020/2021

| 2020/21 | YEAR GROUP |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INTERVENTION | N | R | 1 | 2 | 3 | 4 | 5 | 6 | ESTIMATED COST (£) |  |
| Reading intervention |  |  |  |  | ✓ | ✓ |  |  | 8,302 |  |
| Fresh Start Reading Programme |  |  |  |  |  |  | ✓ | ✓ | 6,973 |  |
| Reading Volunteers (administrative costs) | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 500 |  |
| Boosting Reading Potential |  |  | ✓ | ✓ |  |  |  |  | 2,368 |  |
| Snap on to Maths |  |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 11,840 |  |
| 1st Class @ Numbers |  |  |  |  |  | ✓ |  |  | 1,232 |  |
| 1:1 and small group target work | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |  | 52,943 |  |
| ‘3rd Teacher’ intervention |  |  |  |  |  |  |  | ✓ | 22,718 |  |
| PSHE and Circle Time Training | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 1,138 |  |
| Emotional and Literacy Support Assistants (ELSA) | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 11,401 |  |
| ‘NELI’ – Language support in the Foundation Stage |  | ✓ |  |  |  |  |  |  | 4,210 |  |
| Phonics & Spelling support |  |  |  |  | ✓ | ✓ | ✓ | ✓ | 6,932 |  |
| Therapeutic story writing |  |  |  |  |  |  | ✓ | ✓ | 789 |  |
| DELIGHT project |  |  |  |  | ✓ | ✓ | ✓ |  | 0 (c/f from 19/20) |  |
| HSLW & Supervision | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 43,299 |  |
| Breakfast Club |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 7,560 |  |
| Lunchtime Club |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 3,934 |  |
| Edukey Licence | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 833 |  |
| Inclusion Welfare Officer support (IWO) | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 2,360 |  |
| STIP (Specialist Teachers for Inclusive Practice) support | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 2,910 |  |
| Study Bugs software licence | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 1,025 |  |
| PSHE Association Membership |  |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 125 |  |
| TOTAL COST |  |  |  |  |  |  |  |  |  | £193,392 |
| PUPIL PREMIUM RECEIVED inc LAC Estimated EARLY YEARS PUPIL PREMIUM Estimated |  |  |  |  |  |  |  |  |  | £189,645 £3,713 |
| DIFFERENCE – supplemented by budget |  |  |  |  |  |  |  |  |  | £34 |

Actual spend for the year 2020/2021

| 2020/21 | YEAR GROUP |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INTERVENTION | N | R | 1 | 2 | 3 | 4 | 5 | 6 | ESTIMATED COST (£) |  |
| Reading intervention |  |  |  |  | ✓ | ✓ |  |  | 8,302 |  |
| Fresh Start Reading Programme |  |  |  |  |  |  | ✓ | ✓ | 6,973 |  |
| Reading Volunteers (administrative costs) | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 500 |  |
| Boosting Reading Potential |  |  | ✓ | ✓ |  |  |  |  | 2,368 |  |
| Snap on to Maths |  |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 11,840 |  |
| 1st Class @ Numbers |  |  |  |  |  | ✓ |  |  | 1,232 |  |
| 1:1 and small group target work | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |  | 52,943 |  |
| ‘3rd Teacher’ intervention |  |  |  |  |  |  |  | ✓ | 22,718 |  |
| PSHE and Circle Time Training | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 1,138 |  |
| Emotional and Literacy Support Assistants (ELSA) | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 11,401 |  |
| ‘NELI’ – Language support in the Foundation Stage |  | ✓ |  |  |  |  |  |  | 4,210 |  |
| Phonics & Spelling support |  |  |  |  | ✓ | ✓ | ✓ | ✓ | 6,932 |  |
| Therapeutic story writing |  |  |  |  |  |  | ✓ | ✓ | 789 |  |
| DELIGHT project |  |  |  |  | ✓ | ✓ | ✓ |  | 0 (c/f from 19/20) |  |
| HSLW & Supervision | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 43,299 |  |
| Breakfast Club |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 7,560 |  |
| Lunchtime Club |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 3,934 |  |
| Edukey Licence | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 833 |  |
| Inclusion Welfare Officer support (IWO) | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 2,360 |  |
| STIP (Specialist Teachers for Inclusive Practice) support | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 2,910 |  |
| Study Bugs software licence | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 1,025 |  |
| PSHE Association Membership |  |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 125 |  |
| TOTAL COST |  |  |  |  |  |  |  |  |  | £193,392 |
| PUPIL PREMIUM RECEIVED inc LAC Estimated EARLY YEARS PUPIL PREMIUM Estimated |  |  |  |  |  |  |  |  |  | £189,645 £3,713 |
| DIFFERENCE – supplemented by budget |  |  |  |  |  |  |  |  |  | £34 |